## Sheet1
|  |  | Date: | 2009-10-14
Service Request
Trade/Supplier: |  | Pratt Service
|  |  | Homeowner: |  | Pavel Danilov & Svetlana Danilova
Site: |  | Maplewalk | Daytime #: |  | 416-409-2905
Lot: |  | 57 | Cell:
Address: |  | 1490 Rankin Way | Evening #: |  | 294-0592
Innisfil
NOTE:
Item | Description
1 | The bottom left corner of the center basement window is broken. Replace the awning window sash.
2 | Dig down to reveal the point where the hydro conduit enters the building to confirm that the opening has been sealed.
3 | Fill void in foundation at the left side of the center column between the two garage overhead doors.
Prime and paint the structural steel grey to match the foundation.
4 | Dark brown caulk required at the top of the bottom step flashing near the front eave on the garage roof.
5 | Complete repair to garage side of garage man door and apply one coat of paint to hide repairs.
6 | Owner says the temp is not consistent throughout the home.
Please test temp in room over garage and in basement & complete a “Cold Room Evaluation Doc”.
7 | Skim drywall repair on the bottom of the wall to the left of the stairs up.
8 | Oak ¼ round trim missing at the bottom of the stairs.
9 | Main Bath door swings open by itself. The door to bedroom 2 also shut by itself.
10 | The back panel in the en-suite bath vanity is damaged. Cover the panel with a white end-skin.
11 | There are gaps between the oak ¼ round on both sides of the top flight of stairs and the stringersbeneath
them. Re-set the ¼ round to close the gap. There is also a gap between the top edge of the left stringer
and the nosing above it. Trim the gap.
Confirmation of completion is required by fax 705-735-6991 to Pratt Service Department.
Work must be completed within two weeks of receipt of this work order
unless an appointment date is specified.
If no appointment is specified, it is your responsibility to book an appointment
with this homeowner.